WINDANSEA COCONUTS — RUN OF SHOW

OluKai | Palm Tree Music Festival Montecito — Villa Activation

| Dates: Saturday, October 10 & Sunday, October 11, 2026 (load-in Friday, October 9) Service: 3:00 PM – 10:00 PM both days, ready by 2:30 PM (doors 3:00 PM) Location: Santa Barbara Polo & Racquet Club, 3300 Via Real, Carpinteria, CA 93013 Service Spot: OluKai sponsor footprint, 20' x 10', on the east fence line of the GA field next to the Crazy Mountain booth, between Staff Check-In and Club Check-In (site map on the ClickUp task) Day-Of Contact: RJ Gonzalez, OluKai, 714-916-6782 Festival Ops: Oliver Fernandez 661-406-9162 · Jessica Tranter 646-509-4549 Total Coconuts: 750 across both days Garnish: Sapphire blue orchids (custom, ordered) Headcount: 2,500 | Brand Stamp Logo OluKai horizontal navy Logo on file in ClickUp Stamp status: ordered. |
| --- | --- |

Entrance & Check-In: Load-in (Friday) goes through the Main Entrance on Via Real only. Check in with Marshalling staff at the main entrance for a load-in parking pass, then you will be sent to Field 3. On show days (Sat & Sun) every staff vehicle, 12-passenger van or smaller, must use the Field 3 entrance at 3355 Via Real, the turn-off just before the main entrance. The main entrance is trucks and large vehicles only on show days. Walk the perimeter walkways to the footprint. Do not cut across the polo fields. Drive slowly, there are horses on the grounds. Call RJ with your ETA.

**DAY-OF-SHOW (DOS) STAFF CREDENTIALS AND PARKING PASSES MUST BE PICKED UP AT THE BOX OFFICE BEFORE SATURDAY. LOAD-IN CREDS DO NOT GET YOU IN ON OCT 10 OR 11. WEAR CREDS AT ALL TIMES AND BRING A GOVERNMENT PHOTO ID.**

PRE-EVENT — FRIDAY, OCTOBER 9 (LOAD-IN DAY)

Time TBD — Warehouse Load

- Load 750 stamped coconuts, orchids, straws, napkins, cart, coolers and the supplies listed below

- Warehouse: 9040 Kenamar Dr, Unit 403, San Diego

- San Diego to Carpinteria is roughly 3.5 to 4 hours without traffic. Plan the departure and Friday night lodging around that

10:00 AM – 3:00 PM — Credentials & Parking Passes

- Box Office at the main festival patron entrance, 3300 Via Real. Primary point of contact picks up DOS staff credentials and DOS parking passes for the whole team

- Missed Friday? Saturday pickup is 7:00 AM – 4:00 PM at the Box Office. Contact Sponsorship Ops in advance if your first arrival is a show day

- Credential name changes closed in Lennd on Wed, Oct 7. Placeholder names were not printed. Any credential issue goes to Oliver directly

Friday — Walk the Footprint

- Check in with Marshalling at the Main Entrance for a load-in parking pass, park in Field 3 (staff parking 7:00 AM – 6:00 PM)

- Find the OluKai 20' x 10' footprint on the site map and meet RJ. He is on site Friday and will give final load-in direction

- Drop heavy items (cart, coolers, signage) Friday if our Lennd advance has a load-in slot. Load-in vehicles follow the Lennd advance, which is closed

EVENT DAY 1 — SATURDAY, OCTOBER 10

11:30 AM — Arrive & Load In

- Field 3 entrance, 3355 Via Real. DOS credentials on, parking pass visible on the dash

- Call RJ on arrival, then move everything to the footprint along the perimeter walkways

12:00 PM — Set Up the Villa Footprint

- Cart, signage, decor and coolers inside the 20' x 10'. Anchor anything freestanding, the site is a natural grass field

- OluKai is capturing email sign-ups by QR code. Set the QR signage at the front of the line so guests scan before they get a coconut

- Ice the coolers and stage the first 50 coconuts

2:30 PM — Service Ready

- 50 coconuts opened and garnished with orchids before doors, the rest open on demand

- Team briefed on the scan-first flow. No alcohol on duty, no cannabis, no drones, stay within festival-designated areas

3:00 PM — Doors / Service Begins

- Serve through 10:00 PM. Pace to roughly 375 coconuts for the day

- Expect a rush before each set change. Biggest crowds ahead of The Chainsmokers (6:50 PM) and Zedd (8:35 PM)

- Grab photos and video for socials, golden hour is the best window

10:00 PM — Service Ends

- Break down service items, count remaining coconuts and orchids for Sunday

- Bag all trash from the footprint. Secure the cart and coolers overnight

EVENT DAY 2 — SUNDAY, OCTOBER 11

12:00 PM — Arrive & Reset

- Field 3 entrance again, DOS credentials and parking pass. Re-ice, restage, restock orchids, straws and napkins

2:30 PM — Service Ready

- 50 coconuts opened and garnished before doors

3:00 PM — Doors / Service Begins

- Serve through 10:00 PM with the remaining coconuts. Biggest crowds ahead of Kygo (7:00 PM) and T-Pain (8:50 PM)

10:00 PM — Service Ends

- Full breakdown of service items. Pack everything that can leave Sunday night

- Remove all trash and debris from the footprint. Nothing may be left on site

LOAD OUT — MONDAY, OCTOBER 12

8:00 AM — Strike

- Load out anytime after 8:00 AM, no scheduling needed. Final sweep of the footprint, then return to the warehouse

Post Event

- Add hours to the 2026 Timesheet

- Confirm final payment received, follow up on invoice if not

- Send RJ event photos and the email sign-up count if we have it

SET TIMES (DOORS 3:00 PM BOTH DAYS, SUBJECT TO CHANGE)

Saturday, October 10

- Gagevuu 3:00–3:40 · Toon 3:40–4:15 · Natalie Jinju 4:20–5:00

- All American Rejects 5:30–6:30 · The Chainsmokers 6:50–8:20 · Zedd 8:35–9:50

Sunday, October 11

- Razi Mars 3:00–3:30 · Izy 3:30–4:05 · Myles O’Neal 4:05–4:50 · Frank Walker 4:50–5:35

- Loud Luxury 5:40–6:40 · Kygo 7:00–8:30 · T-Pain 8:50–9:50

COCONUT BREAKDOWN

| Item | Detail |
| --- | --- |
| Total coconuts | 750 (about 375 per day, split to be confirmed) |
| Opened by start of service | 50 opened on site before doors each day, remainder opened on demand |
| Opened before transport | 0 |
| Garnish | Sapphire blue orchids (custom, ordered) |
| Package | Villa: delivery, live service, premium brand activation |
| Headcount | 2,500 across both days |
| Brand stamp | OluKai horizontal navy. Stamp ordered, confirm it is en route or ready before Friday |
| Setup provided | No. Windansea brings the full footprint |
| Certifications | COI and TMM sent by Harrison |

SUPPLIES

Coconuts & Service

- 750 coconuts, stamped OluKai before transport

- Sapphire blue orchids, 750+ (ordered)

- Straws, 750+

- Napkins, 750+

Tools

- Coconut openers and mallets, knives and wooden cutting board, opening station, scraper

- Coolers for roughly 375 coconuts per day, plus ice (source to be confirmed)

- Drain buckets and strainers

Display & Setup

- Villa cart with Windansea decal, umbrella, Windansea signage

- OluKai signage and QR sign-up sign (confirm whether client supplies or we print)

- Stakes, sandbags or weights to anchor the tent, umbrella and signage on grass

- Tent or shade for the 20' x 10' footprint, if we are providing it

Cleaning & Safety

- Food-safe sanitizer spray, bar towels and paper towels, nitrile gloves

- Floor mat or splash guard, heavy-duty trash bags, hand sanitizer pump, first aid kit

Team

- Aprons, sunscreen, reusable water bottles, light rain jacket, closed-toe outdoor footwear

- Government photo ID and DOS credential for every staffer, worn at all times on site

CONTACTS

Client: RJ Gonzalez, OluKai, 714-916-6782, rgonzalez@olukai.com

Festival Sponsorship Ops: Oliver Fernandez, Palm Tree Crew, 661-406-9162, oliver@palmtreecrew.com (credential and load-in changes)

Festival Sponsorship Ops: Jessica Tranter, Palm Tree Crew, 646-509-4549, jessica@palmtreecrew.com

Windansea: Trent LiVolsi, 732-575-5774

Live BEO: https://windansea.vercel.app/beo/86bc8ujw9

CONFIRM BEFORE FRIDAY

- Staff count and call times for both days

- Lodging Friday and Saturday nights

- Whether our Lennd advance includes a Friday load-in slot and vehicle arrival time

- Ice source each day (warehouse vs. on site) and power needs at the footprint

- Tent or shade for the footprint and overnight storage or security for the cart

- Whether Sunday-night strike is allowed, otherwise Monday after 8:00 AM

- Brand stamp arrival, coconuts stamped before Friday load

- Who is primary point of contact for credential pickup, and that every name is on the credential list

- Coconut split per day (750 total)